Action Planning Form Transition group

This Action plan incorporates all age groups and notes generated by each recorder at each table (4).

| Settings and Needs |
| --- |
| What does the network need? What are our shared concerns? | What are our agreements? What are our disagreements? |
| Diane would like a multi-State meeting regarding workforce initiative so we could each see how it is working. Figure out how we can share resources. Integrating individuals, but funded only for DB. Focus PC Planning Linked to IEP goals Advocating for needs: Student Participation; technology Transportation Needs Environmental Assessment Experiences – focus on community involvement Work Related Skills Advocacy for self; Health Career Exploration Links to Peers Students Use of SD to make decisions Add: Contact with HKNC Rep Summer Camp opportunities Rubric – Relate technology and ages to work Incorporate partnerships into rubric – varies by state (ie: VR, commission, HKNC) Add funding/legal considerations section Need for guide/checklist for families? | Agreement/Disagreement Considerations: Format – too detailed and “wordy” Discussion of 16-21 vs 18-22; best time to start – SEAs won’t support 14-21 ITTI Timeline – content is more simple but a Likert Scale would help look at targeted outcomes Electronic Format – need Jeff****: reduce narratives and consider drop down menu with actual examples College and career readiness – needs definition / what does it actually mean Pg 2: Transition Assessment: *** bullet and checklist Definition and various forms/examples of Self Advocacy/Self Determination: Communication Supports after school What does communication system mean? Transition at age 14 may be a bit early – maybe reword to Travel skills Advocating for Needs – reword to Identifying Transition Skills Variety …. Change to Community Involvement or Community Access (accessing outside agencies) Questions around age ranges IDEA/WIOA/vs. States |
| Other questions you could consider: Should birth – 5 be separated out as a separate group? Has VR changes and the 15% rule been considered in the rubric? Are there disability specialist trainers for university personnel? Age 14 too old to begin discussion of communication Should the change be elementary to middle vs. pre/post age 14 (EI/EC/Elementary/Middle etc.?)…. Network/multistate education development on these topics? What are key experiences in this area that inform the decisions we make or have made? What barriers have we experienced and what have the methods/mechanisms been for overcoming them? State differences |

| Action details |
| --- |
| Goal(s): |
| Activities/outputs | Inputs | Timeline | Commitments/shared Leadership | Who will benefit | How can others contribute |
| Establish work group for age ranges Establish group manager to co – facilitate activities with NCDB Establish timelines for the work and roles and responsibilities of members | Adobe work space Instructional design supports Editing supports | November 2015 November 2015 November 2015 | TWG advisors Linda McDowell (NCDB) Catherine Fowler (NSTTAC) Marcia Klovitz(Pepnet ) Beth Jordan (HKNC) Mark Schalock(NCDB) Teresa Coonts (DB proj) NCDB staff lead Instructional designer Editor | Families DB network Transition Teams | Provide feedback Forum spaces Online engagement |

Resources: What resources will support the activities and outputs?

Collaborations (within the DB network and outside the DB network) Ohio IL (Microboards) (ISBE model with links to resources) LA Pepnet 2 NSTAAC HKNC DCMP Dicapta

Potential partners (those who - implement practice, with authority, with influence over practitioners and families) Foundation fighting Blindness and other private groups National Rehab Association Model Secondary School National Federation of the Blind Vary by state. NCDB/HKNC, other states, VR by state, service provider agencies in state

Existing efforts that could be partnered with (what can they offer, how is it connected to the work, potential shared goals, concepts, vocabulary)

Successful individuals with expertise who can mentor and support others in the network

Events that relate where partnerships, resources, and knowledge could be built Pepnet Capacity Building Summit Spring 2016 NSTTAC Institute Spring 2016 DB Summit Summer 2016 PDM Summer 2016

Communication Plan: How will we continue to communicate and work together? (Structure, roles, technology)

Members will establish communication protocols and decide on the mechanism that suits the group best to utilize technology (google drive, Wiggio, adobe etc.)

Follow up information and activities: What would you do to inform the network and enlist new collaborators?

Forum post – Post Summit updates Blog post Webcast